## Slide 1: Expediting Project Delivery Webinar – Implementing Streamlining Measures
Kate Kurgan, AASHTO
David Williams, FHWA
Peggy Laurenz & Dave Huft, South Dakota DOT
Georgi Celusnek, Florida DOT
December 11, 2017

## Slide 2
Safety: Fostering safer driving through analysis of driver, roadway and vehicle factors in crashes, near crashes, and ordinary driving.
Renewal: Rapid maintenance and repair of the deteriorating infrastructure using already-available resources, innovations, and technologies.
Capacity: Planning and designing a highway system that offers minimum disruption and meets the environmental, and economic needs of the community.
Reliability: Reducing congestion and creating more predictable travel times through better operations.
SHRP2 & Its Focus Areas

## Slide 3: Expediting Project Delivery
Expediting Project Delivery identifies 24 strategies for addressing or avoiding 16 common constraints in order to speed delivery of transportation projects.
Strategies Grouped Under Six Objectives:
  Improve internal communication and coordination;
  Streamline decision-making;
  Improve resource agency involvement and collaboration;
  Improve public involvement and support;
  Demonstrate real commitment to the project; and
  Coordinate work across phases of project delivery.

## Slide 4: Expediting Project Delivery
Strategy | Stage of Project Planning or Delivery |  |  |  | 
 | Early Planning | Corridor Planning | NEPA | Design/ROW/ Permitting | Construction
1. Change-control practices |  |  |  |  | 
2. Consolidated decision council |  |  |  |  | 
3. Context-sensitive design and solutions |  |  |  |  | 
4. Coordinated and responsive agency involvement |  |  |  |  | 
5. Dispute-resolution process |  |  |  |  | 
6. DOT-funded resource agency liaisons |  |  |  |  | 
7. Early commitment of construction funding |  |  |  |  | 
8. Expedited internal review and decision-making |  |  |  |  | 
9. Facilitation to align expectations up front |  |  |  |  | 
10. Highly responsive public engagement |  |  |  |  | 
11. Incentive payments to expedite relocations |  |  |  |  | 
12. Media relations manager |  |  |  |  | 
13. Performance standards |  |  |  |  | 
14. Planning and environmental linkages |  |  |  |  | 
15. Planning-level environmental screening criteria |  |  |  |  | 
16. Programmatic agreement for Section 106 |  |  |  |  | 
17. Programmatic or batched permitting |  |  |  |  | 
18. Real-time collaborative interagency reviews |  |  |  |  | 
19. Regional environmental analysis framework |  |  |  |  | 
20. Risk management |  |  |  |  | 
21. Strategic oversight and readiness assessment |  |  |  |  | 
22. Team co-location |  |  |  |  | 
23. Tiered NEPA process |  |  |  |  | 
24. Up-front environmental commitments |  |  |  |  | 

## Slide 5: Implementation Award Recipients
Arizona Department of Transportation (ADOT)
Arkansas State Highway and Transportation Department (AHTD)
Association of Monterey Bay Area Governments (AMBAG)
California Department of Transportation (Caltrans)
Florida Department of Transportation (FDOT)
Idaho Transportation Department (ITD)
Maricopa Association of Governments (MAG)
Massachusetts Department of Transportation (MassDOT)
Nebraska Department of Roads (NDOR)
South Carolina Department of Transportation (SCDOT)
South Dakota Department of Transportation (SDDOT)
Vermont Agency of Transportation (VTrans)

## Slide 6: SHRP2 on the Web
GoSHRP2 www.fhwa.dot.gov/GoSHRP2
  Apply for Implementation assistance
  Learn how practitioners are using SHRP2 products
SHRP2 @AASHTO http://SHRP2.transportation.org
  Implementation information for AASHTO members
SHRP2 @TRB www.TRB.org/SHRP2
  Research information
FHWA R10 & C19 Websites https://www.fhwa.dot.gov/GoSHRP2/Solutions/Renewal/R10
https://www.environment.fhwa.dot.gov/strmlng/shrp2-c19/default.asp

## Slide 7
David Williams, FHWA
david.Williams@dot.gov
202-366-4074
Kate Kurgan, AASHTO
kkurgan@aashto.org
202-624-3635
AASHTO & FHWA Contacts

## Slide 8: Implementing Streamlining Measures
Peggy Laurenz & Dave Huft
South Dakota Department of Transportation
December 11, 2017

## Slide 9: C19 Assessment Workshop
SDDOT
FHWA SD Division
FHWA Resource Center
USDOT Volpe
Participants
“Constraints”
Conflicting Resource Values
Inability to Maintain Agreement
Insufficient Public Engagement
Lack of Dedicated Staff
Large/Complex Projects

## Slide 10: Strengths & Opportunities
Empowered workforce
Management systems
Scoping process
Public engagement
Open, iterative STIP process
Commitment to process improvement
Strategic planning
Strengths
Challenges & Opportunities
Public communication
ITS process integration
Environmental commitment tracking
Project scheduling
Staff size
Staff turnover
Local gov’t coordination
Risk identification in scoping

## Slide 11: Five Actions
Enhance public interaction
Increase schedule accountability and allocate internal resources
SHRP2 C19
Other
Coordinate with External Partners
    Railroads (R16)
    Utilities (R15B)
  Build Internal & External Capacity
    Training
    Mentoring
    Onboarding
  Improve Scoping

## Slide 12: Public Engagement: Public Meetings
Public meeting workflow
Stronger advertising
Personal outreach
Better preparation
Public meeting survey
Strategies
Survey Topics
Date & Location
How aware of meeting?
Reason for interest
Meeting quality
    Purpose clearly explained
    Information clarity
    Free to comment
    Questions answered
  How to improve?

## Slide 13: Sample Survey Results

## Slide 14: Public Engagement: Landowner Communication Survey
Location & Project
Pre-construction communication
    Nature of work
    Adequately informed
    Opportunity to ask questions, express concerns
Communication during construction
SDDOT staff contact
    Accessible
    Timely
    Accurate
    Courteous
Public meetings
Preferred communication
Did well / Do better
Overall satisfaction

## Slide 15: Project Delivery / Scheduling
SDDOT created a “Project Delivery Office” to place emphasis on timely project delivery
Mission: Ensure all pre-construction projects are delivered to Bid Letting on the schedule intended so we can meet STIP dates

## Slide 16: Understanding
What we know, what we need, what we do….
First Steps: Self Evaluation
  understand our processes
  understand our priorities
  identify our strengths
  acknowledge our challenges
  evaluate our scheduling tool
Determine a direction – Make a plan

## Slide 17: Accurate & Reliable Schedules
Become proficient with our scheduling software
    Schedulers attended software training
Involve subject matter experts
    Involve those who are Doing the work
Retool all of our base network schedules
Convert active projects from old schedules to improved networks and redefine schedules for each project
    No more guessing
    Up-to-date, accurate schedules

## Slide 18: Realign Focus: Ready Date Concept
Ready Date: completed plan package due in Bid Letting
New schedules focus on day-to-day work and accomplishing specific activities on time
The new end goal: Ready Date
  on the shelf early
  optimal letting window
  bid letting flexibility
  STIP agility
  meet STIP funding and timing goals

## Slide 19: Long Term Planning to Achieve Short Term Goals
We Knew
  meeting a Project Ready Date and anticipated STIP year takes organization and focus
We Created
  a number of tools ensure each project schedule was getting individual attention at regular intervals
We Can Now
  address project and schedule issues early
  make conscious decisions about the future of the project
  make conscious decisions about the STIP

## Slide 20: Tools for Success
Resource Planning and Allocation
    Manpower availability
Schedule Review Points
    Individual attention and project updates
Project Risk Status
    Status alert system – Red/Yellow/Green
Team Meetings
    The right people in the room for the best decision
Strategic Milestones
    Measure: knowledge is power
Project Delivery Work Group
    “Think Tank”

## Slide 21: Next Steps
Strong focus on communication
Continue to learn and use the software to our advantage
Implement more defined project controls
Clarify roles and responsibilities
Project management training
Provide more management reports and data.
Make conscious and informed decisions.
Possibilities are many. Every step forward or new concept opens the door to more ideas and concepts.

## Slide 22: Streamlining Project Delivery getting to construction sooner
December 2017
Georgi Celusnek, Florida DOT

## Slide 23: How We Got Here
Value Engineering of PD&E
Summer 2013
SHRP2/C-19 Assistance
Fall 2013
SWAT Teams
Spring 2015
NEPA Assignment
December 2016
SWAT is a Process
Measuring Progress

## Slide 24: Recommendations and Implementation
Maximize number of Projects Using State Funds Only
Overlap the PD&E and Design Phases
More Contractual Options for PD&E and Final Design
Designate a Single Project Manager for Both PD&E and Final Design Phases
Perform Pre-Work In Advance of PD&E Study Commencement
Streamline the PD&E and Design Schedule Templates
Perform a Value Engineering Study on the Right of Way Acquisition Process
Hold Pre-Scoping Meeting Workshops for PD&E Projects
Create a PD&E QA/QC Checklist for Final Documents
Standardize Format for PD&E Project Progress Reports
Hold In-Person Regional Training Conferences for FDOT Staff and Consultants
Improve the Public Involvement Program (PIP) Template
Simplify and Combine PD&E Documents
Create PD&E Staffing Hour Guideline Spreadsheet and Estimation Form

## Slide 25: Getting to Construction Sooner in 14 easy steps!
Maximize number of Projects Using State Funds Only
Our Flow Chart to Determine Eligibility

## Slide 26
2. Overlap the PD&E and Design Phases
Getting to Construction Sooner in 14 easy steps!

## Slide 27: Getting to Construction Sooner in 14 easy steps!
PD&E
And
Design
Or PD&E with an optional service for Design
PD&E
Design
3. More Contractual Options for PD&E and Final Design

## Slide 28: Getting to Construction Sooner in 14 easy steps!
4. Designate a Single Project Manager for Both PD&E and Final Design Phases

## Slide 29: Getting to Construction Sooner in 14 easy steps!
5. Perform Pre-Work In Advance of PD&E Study Commencement

## Slide 30: Getting to Construction Sooner in 14 easy steps!
36 to 27 months
6. Streamline the PD&E and Design Schedule Templates

## Slide 31: Getting to Construction Sooner in 14 easy steps!
7. Perform a Value Engineering Study on the Right of Way Acquisition Process

## Slide 32: Getting to Construction Sooner in 14 easy steps!
8. Hold Pre-Scoping Meeting Workshops for PD&E Projects

## Slide 33: Getting to Construction Sooner in 14 easy steps!
9. Create a PD&E QA/QC Checklist for Final Documents

## Slide 34: Getting to Construction Sooner in 14 easy steps!
10. Standardize Format for PD&E Project Progress Reports

## Slide 35: Getting to Construction Sooner in 14 easy steps!
11. Hold In-Person Regional Training Conferences for FDOT Staff and Consultants

## Slide 36: Getting to Construction Sooner in 14 easy steps!
12. Improve the Public Involvement Program (PIP) Template

## Slide 37: Getting to Construction Sooner in 14 easy steps!
13. Simplify and Combine PD&E Documents

## Slide 38: Getting to Construction Sooner in 14 easy steps!
14. Create PD&E Staffing Hour Guideline Spreadsheet and Estimation Form

## Slide 39: Summary

## Slide 40: Questions?
Please remember to type in your questions to the question prompt.
Thank you for participating!

## Slide 41
Dave Huft
South Dakota DOT
Dave.Huft@state.sd.us
575-525-7349
Peggy Laurenz South Dakota DOT 605.773.3654 peggy.laurenz@state.sd.us
Georgi Celusnek
Florida DOT
Georgi.Celusnek@dot.state.fl.us
954-777-4368
Kate Kurgan, AASHTO
kkurgan@aashto.org
202-624-3635
David Williams, FHWA
david.Williams@dot.gov
202-366-4074
Presenter Contacts